# SenseConnect — EshSpeaks Platform Build

## 5-Week Sprint Plan (FE/BE Split + API Contracts)

Prepared by: SenseConnect Dev Team Client project: EshSpeaks LLP platform build Tracking: Trello (board setup in Section B)

Supersedes the 3-week version. Same scope, more room — the custom CMS build (no Ghost) now gets its own dedicated week instead of being crammed into Sprint 1.

## Cadence

- Daily standup (15 min): shipped yesterday / shipping today / blockers

- Weekly review (Fri): demo working software against that week's deliverable, update board, carry over unfinished tickets with a reason

- Client checkpoint (Fri, after internal review): short demo + written status (done / in progress / blocked / cut)

Board columns: Backlog → In Progress → In Review → Client-Ready → Done, tagged by layer (Content / Identity / Commerce / Engagement / Distribution).

## Sprint 1 (Week 1) — Data Model, Auth, Roles, Routing Shell

Goal: the skeleton both tracks build on — locked API contracts, working auth, navigable (empty) routing.

| # | Ticket | Owner |
| --- | --- | --- |
| 1.1 | Repo, environments (dev/staging), CI/CD, hosting + CDN | BE |
| 1.2 | Core data model + migrations: User, Article, Section/Subsegment, Comment, Like, Share, Subscription, NewsletterPreference, PreferenceEvent, FeedSource, AdSlot, LeadCapture | BE |
| 1.3 | Auth: email/password (hashed+salted) + Google OAuth, session/JWT issuance | BE |
| 1.4 | Role + permission middleware, all 8 roles (Chief Editor holds admin access — no separate Admin role) | BE |
| 1.5 | /me endpoint (role, tier, preferences) | BE |
| 1.6 | Freeze Sprint 1 API contracts (see Section A below) before FE starts consuming | BE + FE |
| 1.7 | Login/register forms, OAuth redirect flow | FE |
| 1.8 | App shell: routing for hub, 8 sections, subsegment feeds, article template (static/mock data) | FE |
| 1.9 | Mobile-first layout system, design tokens | FE |

Deliverable: staging link — register/login works, all routes resolve (placeholder content), role-based nav visibility.

## Sprint 2 (Week 2) — Custom CMS: Content Model + Editorial UI

Goal: the CMS the spec assumed Ghost would provide, built from scratch. This is the week that got room to breathe.

| # | Ticket | Owner |
| --- | --- | --- |
| 2.1 | Article content model: draft→review→publish state machine, tier/source-type/sector-tag fields | BE |
| 2.2 | Article CRUD API, image upload/storage pipeline, draft/autosave endpoints | BE |
| 2.3 | Publish + role-gated approval endpoints (contributor → section lead → editor) | BE |
| 2.4 | Meta title/description/canonical auto-generation, Open Graph tags, schema.org Article markup | BE |
| 2.5 | Sitemap.xml + robots.txt generation on publish | BE |
| 2.6 | Freeze Sprint 2 content contracts | BE + FE |
| 2.7 | Editor UI: Markdown-first editor (not full WYSIWYG — keeps this from eating the sprint), media picker, autosave indicator | FE |
| 2.8 | Draft/preview mode | FE |
| 2.9 | Review/approve UI per role (section lead queue, editor override) | FE |
| 2.10 | Real article rendering on hub/section/subsegment/article pages (swap out mock data) | FE |

Deliverable: a section lead can draft, submit, review, and publish a real article that renders correctly across hub → section → subsegment → article.

## Sprint 3 (Week 3) — Membership, Paywall, Payments, Engagement

Goal: the money layer and the interaction layer, together since gating touches both.

| # | Ticket | Owner |
| --- | --- | --- |
| 3.1 | Tier/gating resolution: server-side check on every gated article request, returns preview vs. full body | BE |
| 3.2 | Paystack integration: monthly/annual checkout, webhook handling | BE |
| 3.3 | Subscription status check, server-side, never cached | BE |
| 3.4 | Likes (1/account/article), comments (threaded, flagged-keyword hold, moderation queue), shares (event logging) | BE |
| 3.5 | Feedback endpoint ("was this useful") | BE |
| 3.6 | Freeze Sprint 3 contracts (gated-article shape, subscribe/webhook flow, engagement endpoints) | BE + FE |
| 3.7 | Paywall UI: preview + PREMIUM panel, rendered exactly per API response | FE |
| 3.8 | Subscribe/upgrade UI, plan selection, payment redirect | FE |
| 3.9 | Like button, comment form + thread rendering + pending-moderation state, native share buttons (WhatsApp/X/FB/LinkedIn/copy link) | FE |
| 3.10 | Feedback widget | FE |

Deliverable: register → hit paywall → subscribe → paywall lifts → comment/like/share, all working end to end.

## Sprint 4 (Week 4) — The Seat, Newsletter, Preference Tracking, Ads

Goal: the lead-gen funnel, communications, and monetization-adjacent pieces.

| # | Ticket | Owner |
| --- | --- | --- |
| 4.1 | LeadCapture endpoint: create/update on form submit, trigger 6-email nurture sequence, generate PDF delivery link, log source/attribution | BE |
| 4.2 | Print-request endpoint → fulfilment task | BE |
| 4.3 | Newsletter: general + curated (section-level) subscription logic, ConvertKit sync | BE |
| 4.4 | Preference event ingestion (views, scroll depth, likes, shares, comments, search) for logged-in + anonymous | BE |
| 4.5 | Ad slot resolution: targeting by section/sector, tier-based suppression for premium | BE |
| 4.6 | Freeze Sprint 4 contracts | BE + FE |
| 4.7 | The Seat landing page (own template, no nav/ads), 3-field capture form, print-request form | FE |
| 4.8 | Newsletter opt-in UI (footer + account settings) | FE |
| 4.9 | Client-side event firing for preference tracking | FE |
| 4.10 | Ad slot rendering: leaderboard, in-feed native, sidebar, sponsored segment banner | FE |
| 4.11 | "Recommended for you" / "Trending" modules (basic version, off preference data) | FE |

Deliverable: The Seat funnel works end to end (form → PDF + nurture email), newsletter signup works, ads render and disappear for premium accounts.

## Sprint 5 (Week 5) — Aggregation, Ticker, Admin, SEO Polish, QA, Launch Prep

Goal: feature-complete staging build, client sign-off ready.

| # | Ticket | Owner |
| --- | --- | --- |
| 5.1 | RSS polling ingestion + auto-tagging | BE |
| 5.2 | YouTube Data API ingestion for configured channels | BE |
| 5.3 | Social polling (API where available) + manual curation fallback | BE |
| 5.4 | Market ticker: data API integration, 60s poll during trading hours, static last-close otherwise | BE |
| 5.5 | Admin endpoints: user/role management, subscription records, ad slot config, feed source config, comment moderation, analytics aggregation | BE |
| 5.6 | Related-articles query (by shared tags/subsegment), backlink/syndication feed with canonical tags | BE |
| 5.7 | Rate limiting, HTTPS enforcement, NDPA data export/deletion endpoints | BE |
| 5.8 | Caching layer + Core Web Vitals performance pass | BE + FE |
| 5.9 | Section-lead review queue UI (approve/edit/reject aggregated content) | FE |
| 5.10 | Ticker component: scrolling strip, direction indicators, market-subsegment placement + optional footer strip | FE |
| 5.11 | Admin dashboard UI: all Section 5.5 endpoints get views | FE |
| 5.12 | Related articles module, footer internal linking | FE |
| 5.13 | Image optimization, lazy loading, bundle size pass | FE |
| 5.14 | Full cross-role, cross-tier QA pass + bug fixes | BE + FE |
| 5.15 | Client walkthrough + launch checklist | BE + FE |

Deliverable: full staging walkthrough of every layer in the spec, launch checklist, punch list of anything deferred.

## Risks

- Paystack KYC/approval — start in Week 1, not Week 3

- Market data API vendor access/licensing — confirm and get keys in Week 1

- YouTube/social API credentialing — start early, can have its own lead time

- Editor scope creep in Sprint 2 — hold the line on Markdown-first; a full WYSIWYG block editor can eat the whole sprint on its own

# Section B — Trello Setup

Board name: SenseConnect — EshSpeaks Build

### Lists (left to right)

- Backlog — every ticket from all 5 sprints, added up front

- Sprint [current] — this week's tickets only, pulled from Backlog each Monday

- In Progress

- In Review — PR open / awaiting the other track's sign-off on a shared contract

- Client-Ready — demoable, done pending Friday walkthrough

- Done

### Labels

- 🔵 BE / 🟢 FE / 🟣 Shared — matches the Owner column in every sprint table above

- Sprint 1–5 — one color per sprint, so Backlog stays sortable by week even before cards move

- 🔴 Blocked — pair with a comment tagging who/what it's blocked on

- ⚫ Contract Freeze — the six 1.6/2.6/3.6/4.6-style tickets; keep these visible since they gate parallel work

### Card format

- Title: [Sprint#.Ticket#] Short description (e.g. [2.3] Publish + role-gated approval endpoints)

- Description: paste the one-line ticket text from this doc

- Checklist: break down sub-tasks as the ticket gets picked up

- Due date: end of that ticket's sprint week

- Attach the relevant API contract snippet (Section A) directly on cards that implement or consume an endpoint, so FE/BE aren't hunting through this doc mid-sprint

### Suggested rhythm

- Monday: move the week's tickets from Backlog → Sprint list

- Daily standup: walk the board top to bottom, not person by person — surfaces blockers faster

- Friday: anything not in Client-Ready gets a comment explaining why, then either carries into next week's Sprint list or back to Backlog if scope shifted

Base path: /api/v1. JSON throughout. Auth via session cookie or JWT (BE's call — FE never touches password hashes or tier logic, only reads /me).

| Endpoint | Method | Description/Parameters | Response |
| --- | --- | --- | --- |
| Auth |  |  |  |
| /auth/register | POST | body: { name, email, password } | 201 { user: { id, name, email, role, tier } } |
| /auth/login | POST | body: { email, password } | 200 { user: { id, name, email, role, tier } } |
| /auth/google/redirect | GET | OAuth flow | Redirect |
| /auth/google/callback | GET | Callback for OAuth | Sets session, redirects |
| /me | GET | Current user info | 200 { id, name, email, role, tier, sectionPreferences, newsletterSubscriptions } |
| Articles |  |  |  |
| /sections | GET | List all sections | 200 [{ id, name, slug, isSponsored, subsegments }] |
| /sections/:slug/:subsegmentSlug? | GET | Get section/subsegment feeds | 200 { section, articles: [ArticleSummary], pagination } |
| /articles/:slug | GET | Get full article details (gated server-side) | 200 { id, headline, access, body, relatedArticles } |
| /articles | POST | Create new article [contributor+] | 201 Article Object |
| Membership & Payments |  |  |  |
| /subscriptions/checkout | POST | body: { plan: "monthly" ¦ "annual" } | 200 { checkoutUrl } |
| /subscriptions/status | GET | Check current subscription | 200 { tier, status, renewalDate } |
| Engagement |  |  |  |
| /articles/:id/like | POST | Toggle like on article | 200 { liked: bool, likeCount } |
| /articles/:id/comments | POST | body: { body, parentCommentId? } | 201 { id, status: "pending" ¦ "approved" } |
| The Seat (Lead-Gen) |  |  |  |
| /the-seat/capture | POST | body: { name, email, roleOrInterest } | 200 { downloadUrl, message } |
| Newsletter |  |  |  |
| /newsletter/subscribe | POST | body: { listType, sectors? } | 200 {} |
| Admin |  |  |  |
| /admin/users/:id | GET/PUT | Manage user roles [chief_editor] | 200 User Object |

Note: these contracts are a starting shape to unblock parallel work in Week 1 — freeze the final version per-sprint per the tickets above (1.6, 2.6, 3.6, 4.6) rather than treating this section as immutable on day one.